## Sheet1
No. | Product Deliverables | Task | DucTH | ThanhHC | KhoaLVD | TamNT | Man-day
1 | Report1 - Introduction | Project introduction |  | O |  |  | 1
|  | Current situation |  | O |  |  | 1
|  | Problem definition |  |  |  | O | 1
|  | Proposed solution |  |  |  | O | 1
|  | Feature functions | O | O |  |  | 2
|  | Advantages and disadvantages |  |  | O |  | 1
|  | Functional requirement | O |  |  |  | 2
|  | Review and merge document | O |  |  |  | 2
2 | Report2- Software Project Management Plan | Problem definition |  |  |  | O | 1
|  | Project organization | O |  |  |  | 1
|  | Project management plan | O |  |  |  | 2
|  | Coding Convention |  |  | O |  | 1
|  | Review and merge document | O |  |  |  | 2
3 | Report 3- Software Requirement Specification | User Requirement Specification |  | O |  |  | 2
System Requirement Specification
|  | External interface requirements |  |  | O |  | 1
|  | System overview use case |  | O |  |  | 3
List of use cases
|  | <Guest> Log in/Log out |  |  |  | O | 0.25
|  | <Guest> Sign up |  |  |  | O | 0.25
|  | <Guest> Recover password |  |  |  | O | 0.25
|  | <Guest> Search vehicle |  |  |  | O | 0.75
|  | <Guest> View vehicle's information |  |  |  | O | 0.25
|  | <Authenticated user> Log out |  |  |  | O | 0.25
|  | <Authenticated user> Change password |  |  |  | O | 0.25
|  | <Authenticated user> Change personal information |  |  |  | O | 0.25
|  | <Authenticated user> Search vehicle |  |  |  | O | 0.75
|  | <Authenticated user> View vehicle's information |  |  |  | O | 0.25
|  | <Customer> Book vehicle | O |  |  |  | 0.5
|  | <Customer> View booking history | O |  |  |  | 0.25
|  | <Customer> View detailed booking information | O |  |  |  | 0.25
|  | <Customer> Cancel booking | O |  |  |  | 0.25
|  | <Customer> Comment and rate booking | O |  |  |  | 0.25
|  | <Customer> Register providership | O |  |  |  | 0.5
|  | <Provider> Create vehicle |  |  | O |  | 0.5
|  | <Provider> Duplicate existed vehicle |  |  | O |  | 0.5
|  | <Provider> Edit vehicle |  |  | O |  | 0.5
|  | <Provider> Delete vehicle |  |  | O |  | 0.25
|  | <Provider> View vehicle's booking schedule |  |  | O |  | 0.25
|  | <Provider> View garage's booking schedule |  |  | O |  | 0.25
|  | <Provider> Book own vehicle |  |  | O |  | 0.25
|  | <Provider> Cancle self-booking |  |  | O |  | 0.5
|  | <Provider> Create garage |  | O |  |  | 0.5
|  | <Provider> Edit garage |  | O |  |  | 0.5
|  | <Provider> Close garage |  | O |  |  | 0.25
|  | <Provider> Reopen garage |  | O |  |  | 0.25
|  | <Provider> Add vehicle to garage |  | O |  |  | 0.25
|  | <Provider> Move vehicle to another garage |  | O |  |  | 0.25
|  | <Provider> Create vehicle group |  | O |  |  | 0.5
|  | <Provider> Delete vehicle group |  |  |  | O | 0.25
|  | <Provider> Edit vehicle group |  | O |  |  | 0.5
|  | <Provider> Deactive vehicle group |  |  |  | O | 0.25
|  | <Provider> Reactive vehicle group |  |  |  | O | 0.25
|  | <Provider> Add vehicle to group |  |  |  | O | 0.25
|  | <Provider> Remove vehicle from group |  |  |  | O | 0.25
|  | <Provider> Move vehicle from group |  |  |  | O | 0.25
|  | <Provider> View reports |  |  | O |  | 0.5
|  | <Provider> Extend providership |  |  | O |  | 0.5
|  | <Admin> View reports |  |  |  | O | 0.5
|  | <Admin> Deactive user |  |  |  | O | 0.25
|  | <Admin> Reactive user |  |  |  | O | 0.25
|  | Software System Attribute |  | O |  |  | 1
|  | Conceptual Diagram |  | O | O |  | 2
|  | Review and merge document |  | O |  |  | 2
4 | Report 4- Software Design Description | System architecture design | O |  |  |  | 1
|  | Component diagram |  | O | O |  | 1
|  | Class diagram |  | O |  |  | 2
Interactive diagram
|  | Sequence diagram | O | O | O | O | 2
|  | Activity diagram | O | O | O | O | 2
|  | User interface design | O | O | O | O | 2
|  | Database design | O | O | O | O | 2
|  | Review and merge document | O |  |  |  | 2
5 | Report 5 - Software Implementation and Test Document | Database relationship diagram |  |  |  | O | 2
|  | Test plan | O |  |  |  | 1
|  | Test cases |  | O |  |  | 1
|  | Review and merge document | O |  |  |  | 2
6 | Report 6 - Software User's Manual | Installation Guide | O |  |  |  | 1
|  | User’s Guide |  | O |  |  | 1
|  | Review and merge document | O |  |  |  | 1
7 | Database | Design database | O | O | O | O | 11
|  | Review database | O | O | O | O | 1
8 | Architecture | Design project structure | O |  |  |  | 2
|  | Apply framework & design pattern | O |  | O |  | 2
9 | Implementation | Implement database | O |  |  | O | 5
|  | Guest functions | O |  |  | O | 20
|  | Authenticated user functions | O |  |  |  | 10
|  | Customer functions | O |  |  |  | 30
|  | Provider functions |  | O | O | O | 25
|  | Admin functions |  |  |  | O | 10
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C16: phuong: Use bold format for tasks which have sub-tasks
Note on C17: phuong: Use Indent for sub-tasks